## Critical Path Tests
Three-Point Estimation (TPE)
formula | E = (O + 4*M + P) / 6 |  |  | Module: Teams
Submodule: Teams
E - an estimate (mean value) O - an optimistic best-case scenario P - a pessimistic worst-case scenario M - the most likely scenario
Calculations:
Number of test cases for Critical Path Test to be created |  | 42 | cases
Optimistic best-case scenario for one test case creation (O) |  | 3 | min
Pessimistic worst-case scenario for one test case creation (P) |  | 8 | min
Most likely scenario for one test case creation (M) |  | 5 | min
Average time to create one test case (using the TPE above) |  | E = | 5.1667
Avarage time to create 42 test cases for Critical Path Test |  | E = | 217 |  |  | 3.6167
=
|  |  | minutes |  |  | hours

## First build testing
Work Breakdown Structure (WBS) | [6 empty] | Module: Teams
Submodule: Teams
| Quantity | Time |  |  |  | Total Time | Input Data
Installation: | [5 empty] | 300
Environment | 1 | 240 |  |  |  |  | One test case execution | 5 | min
Application | 1 | 60 |  |  |  |  | Installation: environment | 240 | min
|  |  | Configuration |  |  |  | Installation: application | 60 | min
|  |  | W10, IE | W10, Chrome | W10, Microsoft Edge |  | Test result report | 240 | min
Smoke Tests execution: | 33 | 165 |  |  |  | 495 | Communication | 20%
Module: News | 5 | 25 |  |  |  | 75 | Configurations | 3 | configs
Module: Gallery | 5 | 25 |  |  |  | 75 | Testing Team | 6 | people
Module: Players | 5 | 25 |  |  |  | 75 | One bug report creation | 7 | min
Module: Clubs | 5 | 25 |  |  |  | 75 | One bug reproduction | 5 | min
Module: Teams (Submodule: National Teams) | 8 | 40 |  |  |  | 120 | Average number of confirmed bugs | 49.6 | bugs
Module: Teams (Submodule: Teams) | 5 | 25 |  |  |  | 75 | Bug reports reproduction | 2 | times
Critical Path Tests execution: | 215 | 1075 |  |  |  | 3225
Module: News | 48 | 240 |  |  |  | 720
Module: Gallery | 23 | 115 |  |  |  | 345
Module: Players | 33 | 165 |  |  |  | 495
Module: Clubs | 38 | 190 |  |  |  | 570
Module: Teams (Submodule: National Teams) | 31 | 155 |  |  |  | 465
Module: Teams (Submodule: Teams) | 42 | 210 |  |  |  | 630
Test result report | 1 | 240 |  |  |  | 240
Bug report creation | 49.6 | 7 |  |  |  | 347.2 | Final Calculations
Bug reproduction | 49.6 | 5 |  |  |  | 248 | 1012.3733 | = | 16.8729 | = | 2.1091
Communication | [5 empty] | 971.04 | minutes |  | hours |  | workdays